## Summary
NextXR Digital Twin — Development Status
Status of every capability as of 3 September 2026, verified against the repository rather than the roadmap.
STATUS | COUNT | SHARE | MEANING
RUNS | 28 | 54.9% | Working code, exercisable today against its real input.
PARTIAL | 6 | 11.76% | The mechanism exists but is incomplete or not wired end to end.
BUILT, UNPROVEN | 1 | 1.961% | Complete, tested code that has never run against its real input.
INTENT | 9 | 17.65% | Design only. No implementation.
NOT STARTED | 7 | 13.73% | Identified as needed, no design and no code.
TOTAL | 51
THE ONE-SENTENCE VERSION
The semantic, physics, detection, prediction and agent layers all run today, and real telemetry now flows through the full ingest path from physical hardware. What does not exist: the bridge that lets those measurements correct the twin's own state, a bulk import path, a complete per-tenant delete, enterprise SSO, and any deployed environment.
THE THREE FRAMING FACTS
1. Nothing is deployed. There is no cloud environment running this and no URL.
2. Real telemetry is flowing in — 34,347 samples, 0 rejected — but it does not yet correct the physics. Say 'assimilation is the next module', never that the sensor corrects the twin.
3. Omniverse is zero lines of code, and enterprise SSO is zero lines of code. Both are design intent.

## Status Register
Status Register — every capability, what exists and what is missing
Area | Capability | Status | What exists today | What is missing / next step | Evidence
Core platform | Ontology & semantic graph | RUNS | 273 OWL class declarations across 38 TTL files, held in Neo4j. Ten closed top-level categories, enforced on the ontology itself. | A customer domain outside the shipped packs needs a new pack — a scoped engineering task, not configuration. | nextxr-ontology/platform/, packs/
Core platform | SHACL write gate | RUNS | Every mutation runs validate -> commit -> change log -> bus. Invalid entities are rejected with the violations that caused them. | — | graph/writer.py
Core platform | Tamper-evident change log | RUNS | SHA-256 hash chain with a per-tenant lock so the chain cannot fork. 13,959 real events, 12.1 MB on disk. | Actor ids are not pseudonymised, so right-to-erasure collides with chain integrity. Must be decided before the first customer. | changelog/service.py
Core platform | Twin lifecycle - create / seed / switch | RUNS | 16 twins exist, created from 14 domain templates. Seeded twins are shared to every account so a new login is never empty. | — | twins/service.py, twins/seed.py
Core platform | Twin deletion | PARTIAL | Clears the tenant's Neo4j nodes and its registry row. | Does NOT clear measurements, connector configs, device credentials, scene cache, ownership row or blobs. See the Backlog sheet. | server/twins_routes.py:251
Core platform | Physics runtime | RUNS | 12 dynamics models plus 9 pack physics modules on a ~1 Hz ticker. Engineering-grounded (IEEE C57.91, Peukert, Carnot/IPLV, lumped RC, De Soto five-parameter). | Input is simulated. Real measurements do not drive it — see 'Telemetry to twin state'. | dynamics/models/, packs/*/physics.py
Core platform | Anomaly detection - three tier | RUNS | 17 behaviour modules: threshold, statistical baseline and composite rules, firing on both simulated and real ingested data. | — | behaviors/
Core platform | Findings to diagnosis chain | RUNS | Findings are persisted through the same validated write path; the diagnosis engine correlates them into incidents. | — | twins/coordinator.py
Core platform | Prediction / remaining useful life | RUNS | 8 per-domain prediction modules producing forward projections with confidence bands. | This is physics extrapolation, NOT a trained ML model. Statistical prognostics trained on failure history is not started. | packs/*/predict.py
Core platform | What-if projection | RUNS | Forward-integrates the physics non-destructively over a chosen horizon. | — | POST /twins/{tenant}/project
Core platform | Event bus and live streaming | RUNS | Redis Streams, one per tenant, pushed to the browser over SSE. In-memory fallback when Redis is absent. | Streams are capped at 10,000 entries with no TTL and are not deleted when a tenant is. | bus/event_bus.py
Intelligence | Agentic copilot layer | RUNS | 14 agents across 5 graphs running in-process against the live twin. Falls back to deterministic stubs with no API key, and reports which path a call took. | — | copilot/, agents/
Intelligence | Work order generation | RUNS | Produces a complete, editable work order document from a diagnosis. | — | copilot/agents.py
Intelligence | Work order execution (CMMS loop) | INTENT | Nothing. | No SAP PM, Maximo or ServiceNow integration. The document is produced and then a human carries it. State this explicitly to asset-management buyers. | —
Intelligence | Asset management CRUD | PARTIAL | Full graph CRUD with typed relationships, SHACL-validated and audit-logged. | It is not an EAM: no lifecycle costing, no depreciation, no spares inventory, no scheduling. | server/write_api.py
Data in | Telemetry ingest API | RUNS | HTTP batch and gzipped NDJSON bulk. 207 multi-status with per-sample reasons; idempotent by primary key so a replayed buffer cannot double-count. | — | server/ingest_routes.py, ingest/pipeline.py
Data in | Telemetry historian | RUNS | 34,347 real samples across 8 signals from physical hardware (ESP32 + BME280), 0 rejected. Full path proven: device credential -> validation -> unit normalisation -> quality code -> historian -> bus -> browser. | Changed from BUILT/UNPROVEN on 31 Aug 2026. Retention tiers are configurable but nothing enforces them yet. | data/historian.db, 12.5 MB
Data in | Device credentials | RUNS | Scoped append-only tokens, hash-only storage, rotate and disable per device, optional TTL and asset-prefix narrowing. 1 device registered. | — | ingest/devices.py
Data in | Field connectors - Modbus / OPC-UA / MQTT | BUILT, UNPROVEN | 3,661 lines: Modbus TCP and RS-485 RTU with SunSpec discovery, OPC-UA with subscriptions and browse, MQTT/TLS with Sparkplug B, 7 device profiles. Unit tested. | Never run against real hardware, and pymodbus / paho-mqtt / asyncua are not in requirements.txt. 0 connectors configured. | connectors/
Data in | Point map / tag mapping | PARTIAL | Point maps are validated when saved, not when they decode. Decoder pinned against hand-computed byte patterns in tests. | No UI for uploading or editing a point map — today it is a JSON payload. | connectors/pointmap.py
Data in | Real telemetry driving twin state (assimilation) | INTENT | Nothing. | THE BRIDGE DOES NOT EXIST. Ingested readings reach the historian, the bus and the behaviour rules, but the twin's live frame still comes only from the physics simulation. Highest-value engineering item on the roadmap. | twins/assimilation.py absent
Data in | Bulk asset import (CSV / XLSX) | NOT STARTED | Entities are created one at a time through the validated API. | A mapping step, dry-run validation report and atomic commit. The largest single cost in every onboarding. | —
Data in | History backfill | RUNS | NDJSON bulk endpoint, idempotent, per-sample error reporting. | Volume must be sized with the customer — the historian is a plain table with no compression. | POST /api/v1/ingest/telemetry/bulk
Experience | Web application | RUNS | 90 React components and panels: Twins, Dashboard, Build a Twin, Twin Copilot, Prediction, Change Log. Per-domain dashboards for defence, hospital, EV and rail. | — | frontend/src/
Experience | 3-D scene viewer | RUNS | three.js r169, procedural scenes plus generated GLB models, click-through to live asset state. | — | frontend/src/three/
Experience | 3-D generation - photo to GLB | RUNS | 19-stage reconstruction pipeline; 11 jobs completed. | Depends on an external GPU provider; stubs a marked placeholder mesh without a key. | server/threed_platform/
Experience | BIM / IFC import | PARTIAL | IFC and DXF parsing with discipline-layer semantics; floor plan and CAD to scene via the parser. | Conversion to geometry is the weaker half, and IfcOpenShell is an optional dependency that falls back to synthesis. | agents/ifc_parser.py, agents/bim_support.py
Experience | Marketplace | INTENT | A UI placeholder, marked as such in the navigation config. | Do not demonstrate as working. | frontend/src/nav.js
Experience | XR / headset delivery | INTENT | Nothing. | No code. The 3-D viewer is browser-based. | —
Experience | Omniverse integration | INTENT | Nothing. | ZERO LINES OF CODE. No USD, no Kit, no Nucleus. | OMNIVERSE-AND-TELEMETRY-BRIDGE.md
Security | Multi-tenant isolation | RUNS | Enforced globally at one point. Tenant arrives three ways — query, path and body — and all three are checked. Covered by tests. | — | server/tenancy.py, tests/test_tenant_isolation.py
Security | Identity, organisations, roles | RUNS | Orgs, users, memberships and four ordered roles. Refresh-token sessions with rotation and reuse detection. 2 orgs, 8 owned tenants. | — | identity/
Security | API keys | RUNS | Database-backed, hashed, scoped to an org and optionally a tenant subset, revocable. Never carry the owner role. | — | identity/store.py
Security | Rate limiting | RUNS | Per-principal buckets backed by Redis. | — | server/ratelimit.py
Security | Account audit log | RUNS | Logins, key issuance, role changes and revocations, with actor, IP and user agent. | Holds personal data — needs a retention setting. | identity/store.py
Security | Enterprise SSO (SAML / OIDC / SCIM) | INTENT | Nothing. | A hard dependency for any enterprise customer whose policy mandates SSO. Scope it before signing one. | —
Security | Multi-factor authentication | INTENT | An mfa_secret column exists on the users table. | Nothing writes or checks it. | db/schema.py
Security | Organisation / user deletion | NOT STARTED | Members can be removed and credentials revoked. | There is no delete_org and no delete_user, so personal data cannot be erased through any supported path. | identity/store.py
Offboarding | Per-tenant purge command | NOT STARTED | Two purge functions exist in isolation (historian, change log). | One command that clears every store, with a dry run and a machine-readable receipt. Prerequisite for an honest deletion promise. | —
Offboarding | Historian purge on exit | PARTIAL | historian.purge_tenant() is implemented and documented for erasure requests. | Nothing calls it from the twin deletion path. | historian/core.py:551
Offboarding | Connector and device purge on exit | NOT STARTED | Nothing. | Connector rows hold the customer's PLC and broker passwords and survive tenant deletion. Smallest fix on the list, largest exposure. | —
Offboarding | Tenant attribution for blobs, 3-D jobs, checkpoints | NOT STARTED | These stores are keyed by job id and thread id only. | No tenant column exists, so this data cannot be attributed or purged per customer at all. A schema change plus backfill. | db/schema.py
Offboarding | Data export API | NOT STARTED | Nothing. | Portability is a contract term we cannot currently meet without a bespoke script. | —
Offboarding | Retention enforcement | NOT STARTED | Retention tiers are defined and overridable per deployment. | No cron enforces them; raw telemetry grows unbounded. | historian/schema.py
Offboarding | Backup lifecycle rules | INTENT | Backup procedure is documented (RDS automated backups, Neo4j dumps to S3, EBS snapshots). | No S3 lifecycle rule on the Neo4j dumps, so deleted customer graphs would persist indefinitely. Must be configured before the first customer. | AWS_DEPLOYMENT.md
Operations | Local development stack | RUNS | docker-compose plus a launch script bring up the whole system on a laptop. | — | docker-compose.yml, start.ps1
Operations | Cloud deployment | INTENT | A complete deployment runbook. | NOTHING IS DEPLOYED. No AWS account running this, no URL. Estimated two to four days for one engineer, not started. | AWS_DEPLOYMENT.md
Operations | Structured logging and observability | RUNS | JSON logs with request correlation ids, severity and access logging. | Log retention not set — the default is never expire. | server/observability.py
Operations | Automated tests | PARTIAL | 11 test modules covering auth enforcement, tenant isolation, identity, ingest and historian, point map decoding, migrations, rate limiting and the solar spec. | No end-to-end browser tests; connector tests do not touch hardware. | tests/
Operations | Continuous integration | RUNS | GitHub Actions workflow. | No deployment stage, because there is no deployment. | .github/workflows/ci.yml
Operations | Database migrations | RUNS | Versioned migration chain plus a schema reconciler that adds missing columns on boot. Works on SQLite and MySQL. | — | db/migrations.py, db/schema.py

## Backlog
Backlog — what is yet to be developed, ranked
Ranked by what unblocks a customer commitment first, not by size.
Rank | Item | Area | Rough size | Priority | Why it ranks here
1 | Purge connector and device rows on tenant deletion | Offboarding | Hours | Critical | We currently retain a customer's live PLC and broker credentials after their twin is deleted. Smallest fix on the list, largest exposure.
2 | tools/purge_tenant.py - one command, every store, dry run and receipt | Offboarding | Days | Critical | Turns a twelve-step manual runbook into something rehearsable and auditable. Two of the purge functions already exist.
3 | Add tenant_id to threed_jobs and checkpoints; tenant prefix on blob keys | Offboarding | Days | Critical | Without it three stores cannot be attributed to a tenant, and complete deletion cannot be promised honestly.
4 | Real telemetry driving twin state (assimilation module) | Core platform | Weeks | Critical | The single biggest capability gap. Until it exists, measurements inform the rules but never correct the twin's own physics.
5 | Deploy to a cloud environment | Operations | 2-4 days | Critical | Nothing is deployed. There is no environment to give a customer or an auditor access to.
6 | Bulk asset importer - CSV/XLSX with mapping, dry run and atomic commit | Data in | Weeks | High | The largest single cost in every onboarding, and the difference between a self-serve product and a consulting engagement.
7 | Data export API - the full exit bundle | Offboarding | Weeks | High | Portability is a contract term. It also removes the main reason purges slip past their deadline.
8 | Run the field connectors against real hardware; add the protocol libraries to requirements.txt | Data in | Days | High | 3,661 lines of tested code that has never met a device. pymodbus, paho-mqtt and asyncua are not even installed.
9 | Organisation and user deletion | Security | Days | High | There is no supported path to erase personal data.
10 | Pseudonymised actor ids in the change log | Core platform | Days | High | Makes erasure compatible with the hash chain. Cannot be applied retroactively - decide before the first customer.
11 | Enterprise SSO - SAML / OIDC, then SCIM | Security | Weeks | High | A blocking dependency for enterprise customers, not a nice-to-have.
12 | Retention enforcement cron over the historian tiers | Operations | Days | Medium | Policy exists and is configurable; nothing enforces it. A cost problem before it is a compliance one.
13 | Backup lifecycle rules on Neo4j dumps, EBS snapshots and S3 versions | Operations | Hours | Medium | Without them, 'deleted' data persists in backups indefinitely and the deletion promise is false.
14 | Point map upload and edit UI | Data in | Weeks | Medium | Today a customer's tag map is a JSON payload we hand-craft. This is delivery time on every site.
15 | CMMS / EAM integration - work order execution | Intelligence | Weeks | Medium | 'Work order' reads as closed-loop to an asset-management buyer. Today the document is generated and a human carries it.
16 | Multi-factor authentication | Security | Days | Medium | The column exists; the feature does not.
17 | BIM geometry conversion - the weaker half of IFC | Experience | Weeks | Medium | Parsing works; turning it into good geometry is incomplete.
18 | Marketplace | Experience | Weeks | Low | UI placeholder only. Do not demonstrate as working.
19 | Trained ML prognostics on failure history | Intelligence | Months | Low | Current prediction is physics extrapolation with confidence bands. Needs customer failure history to train on, so it follows onboarding rather than leading it.
20 | Omniverse integration | Experience | Months | Low | Zero lines of code. Scope it as a new project, not an extension.
21 | XR / headset delivery | Experience | Months | Low | No code. The 3-D experience is browser-based today.

## Evidence
Evidence — measured counts, 3 September 2026
Read from the running databases and the source tree, not quoted from a deck.
Measure | Value | Source
Twins registered | 16 | data/twins.db
Domain templates | 14 | twins/service.py TEMPLATES
Domain packs shipped | 12 | packs/ (hvac, cfp, turbine, edm, railway, hospital, ev, solar, defence, fleet, datacenter, bim)
Ontology TTL files | 38 | platform/, packs/, imports/
OWL class declarations | 273 | grep across all TTL
Top-level taxonomy categories | 10 (closed) | platform/nxr-taxonomy.ttl
Change log events | 13,959 | data/changelog.db - 12.1 MB
Telemetry samples stored | 34,347 | data/historian.db - 12.5 MB
Distinct signals ingested | 8 | real hardware, 31 Aug - 1 Sep 2026
Telemetry samples rejected | 0 | ingest validation
Ingest devices registered | 1 | esp32-rig-01
Field connectors configured | 0 | data/connectors.db
3-D reconstruction jobs completed | 11 | data/threed_jobs.db
Organisations | 2 | data/identity.db
Tenants owned by an org | 8 | org_tenants
Python lines of code | 51,757 | nextxr-ontology/, excluding caches
Connector layer lines of code | 3,661 | connectors/
React components and panels | 90 | frontend/src/
Dynamics models | 12 | dynamics/models/
Pack physics modules | 9 | packs/*/physics.py
Pack prediction modules | 8 | packs/*/predict.py
Behaviour / rule modules | 17 | behaviors/
Test modules | 11 | tests/
Deployed environments | 0 | nothing is deployed

## Legend
Legend — what each status means, and how to talk about it
Status | Definition | How to state it
RUNS | Working code, exercisable today against its real input. | Can be demonstrated. Safe to state as a capability.
BUILT, UNPROVEN | Complete, tested code that has never run against its real input. | Do not demonstrate. State as 'written and tested, not yet proven against hardware'.
PARTIAL | The mechanism exists but is incomplete or not wired end to end. | State what works and what does not, in the same sentence.
INTENT | Design only. No implementation. | Never imply it exists. Give the estimate instead.
NOT STARTED | Identified as needed, no design and no code. | A backlog item with an owner, or it will be discovered by a customer.
Rough size is engineering effort for one engineer, excluding review and deployment.